Byrne Acquisition Group LLC

WIFS(TV)

2814 Syene Rd, Madison, WI 53713

608.270.5700

October 18, 2019

Dear FCC:

This exhibit letter is to explain our request for an engineering STA as well as a CP extension to accommodate the usage of an existing WHA antenna on the Madison Community Tower until two issues are resolved. Those two issues are:

1. The new top-mount antenna listed on WIFS’ primary CP is still awaiting install on the tower, currently scheduled for install on approximately 10/24/19. WIFS has discontinued operations on its pre-auction channel and will be operating from the existing top-mount antenna until install is complete.
2. WIFS’ new ch 21 main transmitter’s full-power mask filter was defective and failed during testing last week. The manufacturer is estimating the replacement/install timeline will be at least 2 weeks before full power operation is possible, on approximately 11/1/19, pending the install and testing of the replacement mask filter. WIFS will operate from its auxiliary transmitter operating at 13.1kW ERP until then.

WIFS will continue our best effort in order to complete the facilities installations and begin full power operation as soon as possible.

Sincerely,

Roy Henn – Chief Engineer

[roy@wi57.tv](mailto:roy@wi57.tv) | 608.535.9504